# Faculty of Technology and Engineering

# Chandubhai S Patel Institute of Technology

Department of Computer Science & Engineering

Date: 23 / 09 / 2025

Laboratory Performa

| Academic Year | : | 2022-23 | Semester | : | 5 |
| --- | --- | --- | --- | --- | --- |
| Course code | : | CS301 | Course name | : | Software Engineering |

# Project Overview

  - Type: Employee Management System

  - Tech Stack: MERN Stack(MongoDB, ExpressJS, ReactJS, NodeJS)

  - Key Features: Data storing of all Employee, Manage Employee, Project Management, etc.

# Code Metrics

| Component | Lines of Code |
| --- | --- |
| Backend (JS) | 10,203 |
| Frontend (TS/React) | 20,230 |
| Config (JSON) | 8,915 |
| Docs (Markdown) | 169,283 |
| Executable Code | 26,867 |

- Function Point Analysis (Step-by-Step)

  - External Inputs (EI)

    - Count: 23

    - Simple: 8 × 3 = 24

    - Average: 12 × 4 = 48

    - Complex: 3 × 6 = 18

    - Total EI = 90 FP

  - External Outputs (EO)

    - Count: 18

    - Simple: 6 × 4 = 24

    - Average: 9 × 5 = 45

    - Complex: 3 × 7 = 21

    - Total EO = 90 FP

  - External Inquiries (EQ)

    - Count: 19

    - Simple: 7 × 3 = 21

    - Average: 10 × 4 = 40

    - Complex: 2 × 6 = 12

    - Total EQ = 73 FP

  - Internal Logical Files (ILF)

    - Count: 7

    - Simple: 2 × 7 = 14

    - Average: 4 × 10 = 40

    - Complex: 1 × 15 = 15

    - Total ILF = 69 FP

  - External Interface Files (EIF)

    - Count: 4

    - Simple: 2 × 5 = 10

    - Average: 1 × 7 = 7

    - Complex: 1 × 10 = 10

    - Total EIF = 27 FP

    - Unadjusted FP (UFP) = 90 + 90 + 73 + 69 + 27 = 349

  - Complexity Adjustment Factor (CAF)

    - CAF = 0.65 + (ΣFi / 100)

= 0.65 + (54 / 100)

= 0.65 + 0.54

= 1.19

    - Adjusted FP = UFP × CAF = 349 × 1.19 = 415 F

# COCOMO Calculations

  - Convert FP to LOC

    - Average: 53 LOC/FP for JavaScript

    - LOC = 415 × 53 = 21,995 ≈ 22 KLOC

  - Basic COCOMO Formulae

    - Effort (PM) = 3.0 × (KLOC)^1.12

= 3.0 × (22)^1.12

= 3.0 × 26.4

= 79.2 PM

    - Development Time (TDEV) = 2.5 × (Effort)^0.35

= 2.5 × (79.2)^0.35

= 2.5 × 4.8

= 12.0 Months

    - Team Size = Effort / TDEV

= 79.2 / 12.0

= 6.6 ≈ 7 people

  - Intermediate COCOMO (Effort Multipliers)

    - Effort Adjustment Factor (EAF) = 0.89

    - Adjusted Effort = 79.2 × 0.89 = 70.5 PM

    - TDEV = 12.0 months

    - Team Size = 70.5 / 12 = 6 people

  - Detailed COCOMO (Phase-wise Distribution)

    - Requirements Analysis: 6% → 4.2 PM

    - Product Design: 16% → 11.3 PM

    - Programming: 68% → 47.9 PM

    - Integration & Testing: 10% → 7.1 PM

# Risk Analysis

  - High Risk: OCR accuracy, Real-time sync, Multi-tenant isolation, API dependency

  - Medium Risk: Database performance, Frontend state management, Browser issues

  - Low Risk: CRUD, Static pages

# Final Summary

  - Adjusted FP: 415

  - Estimated LOC: 22K

  - Effort: 70.5 Person-Months

  - Timeframe: 12 Months

  - Team Size: 6 Developers

  - Project Type: Semi-Detached